## Current Iteration
|  | Iteration Number: |  |  |  | 1
|  | Expected Total effort: |  |  |  | 33
|  | Days In Sprint: |  |  |  | 10
Burndown Chart
User Stories |  | Days (Points Completed) | [19 empty] | Remaining
Product Backlog Items | Beginning Balance | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Task Balance | Percentage Completed
API REST elecciones | 8 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 1; Days (Points Completed) 5: 0; Days (Points Completed) 6: 2; Days (Points Completed) 7: 3; Days (Points Completed) 8: 0; Days (Points Completed) 9: 2; Days (Points Completed) 10: 0 | 0 | 100%
Crear modelo de elecciones | 2 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 1; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 1; Days (Points Completed) 7: 0; Days (Points Completed) 8: 0; Days (Points Completed) 9: 0; Days (Points Completed) 10: 0 | 0 | 100%
Crear elección frontend | 8 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 3; Days (Points Completed) 7: 0; Days (Points Completed) 8: 2; Days (Points Completed) 9: 1; Days (Points Completed) 10: 2 | 0 | 100%
Documentacion | 3 | Days (Points Completed) 1: 1; Days (Points Completed) 2: 0; Days (Points Completed) 3: 2; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 0; Days (Points Completed) 8: 0; Days (Points Completed) 9: 0; Days (Points Completed) 10: 0 | 0 | 100%
Test | 5 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 3; Days (Points Completed) 8: 0; Days (Points Completed) 9: 0; Days (Points Completed) 10: 0 | 2 | 60%
Crear modelo votacion | 2 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 0; Days (Points Completed) 6: 0; Days (Points Completed) 7: 0; Days (Points Completed) 8: 2; Days (Points Completed) 9: 0; Days (Points Completed) 10: 0 | 0 | 100%
API REST votacion | 5 | Days (Points Completed) 1: 0; Days (Points Completed) 2: 0; Days (Points Completed) 3: 0; Days (Points Completed) 4: 0; Days (Points Completed) 5: 1; Days (Points Completed) 6: 2; Days (Points Completed) 7: 0; Days (Points Completed) 8: 0; Days (Points Completed) 9: 2; Days (Points Completed) 10: 0 | 0 | 100%
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Effort Remaining | 33 | 32 | 31 | 29 | 28 | 27 | 19 | 13 | 9 | 4 | 2 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 2 | 93.94%
Ideal Trend | 33 | 29.7 | 26.4 | 23.1 | 19.8 | 16.5 | 13.2 | 9.9 | 6.6 | 3.3 | - | - | - | - | - | - | - | - | - | - | -
Note on G4: For an Accurate Burndown Chart and Ideal Trend, Fill in the expected working days in an Iteration (1 Week = 5 Days). You can additionally choose to hide columns that are not needed. If your Iteration is 2 weeks long, you can hide columns M through V and place 10 in this box. Default Formula Assumes 20 days